## MLK
Functionality |  |  | Planned |  | Actual |  | Duration | Guide | Reference | Assignments
System Name | Function Name | Sub Function Name | Start Date | End Date | Start Date | End Date | Effort |  | Documents
Manulink Overview | Overview | About Manulife | 2018-03-23 | 2018-03-23
|  | Overview of AgentWeb | 2018-03-23 | 2018-03-23
|  | Development Environment and Infrastructure | 2018-03-23 | 2018-03-23
|  | Application Development environment Setup | 2018-03-23 | 2018-03-23
|  | DB overview | 2018-03-26 | 2018-03-26
| Architecture | System Technical Architecture (Online) | 2018-03-27 | 2018-03-27
Online
| User Management | New | 2018-03-28 | 2018-03-28
|  | Update | 2018-03-28 | 2018-03-28
|  | Password reset | 2018-03-28 | 2018-03-28
|  | Different Typres of users and previleges | 2018-03-28 | 2018-03-28
| Customer Management | New | 2018-03-29 | 2018-03-29
|  | Update | 2018-03-29 | 2018-03-29
|  | Customer Search | 2018-03-29 | 2018-03-29
| Overview of product | Types of products | 2018-03-30 | 2018-03-30
|  | Products and Sales Channel Mapping | 2018-03-30 | 2018-03-30
|  | Product and Application Mapping | 2018-03-30 | 2018-03-30
|  | Purpose of products | 2018-03-30 | 2018-03-30
|  | Riders and Benefits | 2018-04-02 | 2018-04-02
|  | Premium and Coverage | 2018-04-02 | 2018-04-02
|  | Simulation and Reports | 2018-04-02 | 2018-04-02
| Illustration (Retail) | Illustration Creation\Modification | 2018-04-03 | 2018-04-03
|  | Illustration Search | 2018-04-03 | 2018-04-03
|  | Illustration Calculation (Premium & Commission Incl Valid Term) | 2018-04-04 | 2018-04-04
|  | Illustration Print | 2018-04-05 | 2018-04-05
|  | Illustration Copy | 2018-04-05 | 2018-04-05
|  | Record Lock and Customer History handling | 2018-04-06 | 2018-04-06
|  | Limit Check | 2018-04-06 | 2018-04-06
| Corporate New design & Implementation | Illustration Creation | 2018-04-09 | 2018-04-09
|  | Tab navigation (Switch,save,load) | 2018-04-09 | 2018-04-09
|  | Plan save | 2018-04-09 | 2018-04-09
|  | Premium calculation | 2018-04-09 | 2018-04-09
| Application (Along with new corporate design) | Application Creation\Modification | 2018-04-10 | 2018-04-10
|  | Application Search | 2018-04-10 | 2018-04-10
|  | Application Print | 2018-04-10 | 2018-04-10
|  | Limit Check | 2018-04-10 | 2018-04-10
|  | Application Status Inquiry | 2018-04-10 | 2018-04-10
| Inquiries | Policy Inquiry | 2018-04-11 | 2018-04-11
|  | Movement Status Inquiry | 2018-04-11 | 2018-04-11
|  | Agency Edit | 2018-04-11 | 2018-04-11
|  | Contract Maintainance | 2018-04-12 | 2018-04-12
|  | Doctor Search | 2018-04-12 | 2018-04-12
| Manuals | Documents\Manuals\Guidelines | 2018-04-12 | 2018-04-12
| Search | Agency Search | 2018-04-13 | 2018-04-13
|  | Agent Search | 2018-04-13 | 2018-04-13
|  | Agency Referal Search | 2018-04-13 | 2018-04-13
|  | Version Control | 2018-04-16 | 2018-04-16
|  | Deployment and Release Management | 2018-04-16 | 2018-04-16
Products | Product Info | Product Type (UL/Annuity), Riders, Benefits | 2018-04-17 | 2018-04-17
| Simulation |  | 2018-04-17 | 2018-04-17
| Report Generation | All Reports including Plan and Application | 2018-04-17 | 2018-04-17
| Commission | Including Reports | 2018-04-18 | 2018-04-18
NBOS/IRCC | SOAP Services | Application Lock/Unlock
Get Application Data
Application Data Feed
Application SalesCondition Checking
Application SalesCondition Calculation
Application SalesCondition LimitCheck
Inquiries | Agency Edit | Search, Clear, Detail Display, Update and Code Walk Through
| Policy Inquiry | Search, Clear, Detail Display and Code Walk Through
| Application Status Inquiry | Search, Clear, Send Mail, CSV download, Detail Display, Print and Code Walk Through
| Medical Exam Inquiry | Save, Clear, Assessment and Code Walk Through
| Doctor Search | Search, Select All, UnSelect All, Details List and Code Walk Through
| Contract Maintenance | Search, Clear, Detail Display, Update and Code Walk Through
| Movement Status Inquiry | Search, Print and Code Walk Through
Improvements | Recent Production Issues
Challenges
Performance issues and improvement Plan
Access | Access Preveleges & Roles |  | 2018-04-19 | 2018-04-19
| Channel Access (PA, MGA & FI) |  | 2018-04-19 | 2018-04-19
Reverse KT | Session - 1 |  | 2018-04-20 | 2018-04-20
Session - 2
Hides for corporate KT.